## Gantt Chart
Conflict Intelligence – Project Plan (Gantt Chart)
Ali Hamdy +MIN5_DATA3_S1
All 63 tasks with their owner. Edit the blue Start/End dates and the bars move automatically. Week columns start from the date in I5 (a Monday). Bar colour = owner.
|  | Bar colour = owner: | [5 empty] | Ali |  | Salma |  | Sara |  | Yasmeen |  | Jessy
# | Phase | Task | Owner | Start | End | Days | Status | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07
1 | Planning | GitHub Organization (repository, branching, commit & PR rules) | Ali | 2026-10-05 | 2026-10-09 | 5 | Done
2 | Planning | Literature Review & Gap Analysis | Yasmeen | 2026-10-05 | 2026-10-16 | 12 | Done
3 | Planning | Project Plan & Gantt Chart | Ali | 2026-10-05 | 2026-10-09 | 5 | Done
4 | Planning | Project Proposal (problem statement, objectives, scope, expected outcomes) | Ali | 2026-10-05 | 2026-10-09 | 5 | Done
5 | Planning | Task Assignment & Roles | Ali | 2026-10-05 | 2026-10-09 | 5 | Done
6 | Planning | Risk Assessment & Mitigation Plan | Salma | 2026-10-05 | 2026-10-14 | 10 | In Progress
7 | Planning | Project KPIs (project success KPIs document) | Sara | 2026-10-05 | 2026-10-14 | 10 | In Progress
8 | Planning | Dataset Documentation & Data Dictionary | Jessy | 2026-10-05 | 2026-10-14 | 10 | Done
9 | Planning | Requirements Gathering (stakeholders, functional & non-functional requirements) | Jessy | 2026-10-05 | 2026-10-16 | 12 | In Progress
10 | Planning | Lecturer Feedback & Grading Criteria (ongoing: request now, update after each review) | Ali | 2026-10-05 | 2026-12-04 | 61 | In Progress
11 | Planning | Team Follow-up (weekly check-in, handoffs, status) | Ali | 2026-10-05 | 2026-12-04 | 61 | In Progress
12 | Design | Data Quality Assessment & Data Quality Report | Ali | 2026-10-05 | 2026-10-30 | 26 | Not Started
13 | Design | Architecture & Technology Stack | Salma | 2026-10-05 | 2026-10-23 | 19 | In Progress
14 | Design | Database Design (ER Diagram, Logical & Physical Schema) | Yasmeen | 2026-10-05 | 2026-10-23 | 19 | Not Started
15 | Design | Data Cleaning & Preparation (v0 on 16 Oct, v1 on 23 Oct, final on 30 Oct) | Ali | 2026-10-12 | 2026-10-30 | 19 | Not Started
16 | Design | Analytical Questions & KPI Design (shortlist on 23 Oct; whole team contributes) | Sara | 2026-10-12 | 2026-10-30 | 19 | Not Started
17 | Design | QA: Testing Plan | Jessy | 2026-10-12 | 2026-10-30 | 19 | Not Started
18 | Design | Problem Statement Support, Use Case Diagram & Use Case Descriptions | Jessy | 2026-10-12 | 2026-10-27 | 16 | Not Started
19 | Design | DFD, Sequence, Activity, State & Class Diagrams | Sara | 2026-10-19 | 2026-11-06 | 19 | Not Started
20 | Design | Business Rules & KPI Definitions | Yasmeen | 2026-10-19 | 2026-10-30 | 12 | Not Started
21 | Design | Wireframes, Mockups & UI/UX Guidelines | Jessy | 2026-10-19 | 2026-10-30 | 12 | Not Started
22 | Design | Component Diagram, Deployment Diagram & Deployment Strategy | Yasmeen | 2026-10-28 | 2026-11-06 | 10 | Not Started
23 | Implementation | Python EDA | Ali | 2026-10-16 | 2026-11-13 | 29 | Not Started
24 | Implementation | SQL Analysis (CTEs, window functions, subqueries, ranking, aggregations) | Salma | 2026-10-19 | 2026-11-13 | 26 | Not Started
25 | Implementation | Statistical Analysis | Ali | 2026-10-26 | 2026-11-13 | 19 | Not Started
26 | Implementation | Time-Series, Trend & Seasonality Analysis | Ali | 2026-10-26 | 2026-11-13 | 19 | Not Started
27 | Implementation | Geographic / Spatial Analysis (including geographic SQL) | Salma | 2026-10-26 | 2026-11-20 | 26 | Not Started
28 | Implementation | SQL Analytical Views | Salma | 2026-10-26 | 2026-11-20 | 26 | Not Started
29 | Implementation | Power Query & Power BI Data Model | Sara | 2026-10-26 | 2026-11-13 | 19 | Not Started
30 | Implementation | Database & Data Model Validation | Yasmeen | 2026-10-26 | 2026-11-13 | 19 | Not Started
31 | Implementation | Power BI Data Modeling, Power Query & DAX Support and Validation | Yasmeen | 2026-10-26 | 2026-11-20 | 26 | Not Started
32 | Implementation | Tableau Dashboard Development (calculated fields, filters, actions, geographic visualization, UX) | Jessy | 2026-10-26 | 2026-11-20 | 26 | Not Started
33 | Implementation | SQL Data Validation | Salma | 2026-11-02 | 2026-11-20 | 19 | Not Started
34 | Implementation | Power BI Dashboard Development (slicers, drill-through, tooltips, bookmarks, navigation, UX, performance) | Sara | 2026-11-02 | 2026-11-20 | 19 | Not Started
35 | Implementation | Advanced DAX Measures & KPI Implementation | Sara | 2026-11-02 | 2026-11-20 | 19 | Not Started
36 | Implementation | QA: Test Cases | Jessy | 2026-11-02 | 2026-11-20 | 19 | Not Started
37 | Implementation | Python Documentation | Ali | 2026-11-09 | 2026-11-25 | 17 | Not Started
38 | Implementation | README | Ali | 2026-11-09 | 2026-11-25 | 17 | Not Started
39 | Implementation | SQL Documentation | Salma | 2026-11-09 | 2026-11-20 | 12 | Not Started
40 | Implementation | Cross-Tool Validation (SQL = Python = Power BI = Tableau) | Salma | 2026-11-09 | 2026-11-27 | 19 | Not Started
41 | Implementation | Database Documentation | Yasmeen | 2026-11-09 | 2026-11-20 | 12 | Not Started
42 | Implementation | Source Code Quality & Code Review | Ali | 2026-11-16 | 2026-11-25 | 10 | Not Started
43 | Implementation | Dashboard Insights & Recommendations | Sara | 2026-11-16 | 2026-11-24 | 9 | Not Started
44 | Implementation | Power BI Documentation | Sara | 2026-11-16 | 2026-12-02 | 17 | Not Started
45 | Implementation | Analytical Results (consolidation of findings, key insights, recommendations) | Yasmeen | 2026-11-16 | 2026-11-27 | 12 | Not Started
46 | Implementation | Packaged Final Files | Ali | 2026-11-23 | 2026-11-30 | 8 | Not Started
47 | Final | QA: Bug Tracking & Resolution Verification | Jessy | 2026-11-09 | 2026-12-02 | 24 | Not Started
48 | Final | Tableau / Requirements / QA Documentation and Final Documentation Structure | Jessy | 2026-11-09 | 2026-12-02 | 24 | Not Started
49 | Final | Testing: Python, Data Quality & Cleaning (own area) | Ali | 2026-11-16 | 2026-11-27 | 12 | Not Started
50 | Final | Technical Documentation (with Jessy's support) | Salma | 2026-11-16 | 2026-12-02 | 17 | Not Started
51 | Final | Testing: SQL & Geographic Analysis (own area) | Salma | 2026-11-16 | 2026-11-27 | 12 | Not Started
52 | Final | Power BI KPI Validation & Dashboard Testing (own area) | Sara | 2026-11-16 | 2026-11-27 | 12 | Not Started
53 | Final | Testing: Database & Data Model (own area) | Yasmeen | 2026-11-16 | 2026-11-27 | 12 | Not Started
54 | Final | Final Project Report | Jessy | 2026-11-16 | 2026-12-04 | 19 | Not Started
55 | Final | Tableau Validation (own area) | Jessy | 2026-11-16 | 2026-11-27 | 12 | Not Started
56 | Final | User Manual (Power BI and Tableau dashboards) – provisional owner | Sara | 2026-11-23 | 2026-12-02 | 10 | Not Started
57 | Final | Analytical Results Validation, Limitations & Future Analysis | Yasmeen | 2026-11-23 | 2026-12-02 | 10 | Not Started
58 | Final | QA: End-to-End Testing | Jessy | 2026-11-23 | 2026-12-02 | 10 | Not Started
59 | Final | QA: Dashboard Usability Testing | Jessy | 2026-11-23 | 2026-12-02 | 10 | Not Started
60 | Final | Final Integration & Consistency Check | Ali | 2026-11-25 | 2026-12-04 | 10 | Not Started
61 | Final | Final Presentation (PPT/PDF) | Yasmeen | 2026-11-25 | 2026-12-04 | 10 | Not Started
62 | Final | QA: Reproducibility Testing | Jessy | 2026-11-26 | 2026-12-02 | 7 | Not Started
63 | Final | Video Demonstration (optional) | Salma | 2026-11-30 | 2026-12-04 | 5 | Not Started
Milestones (official deadlines)
◆ | Milestone | Planning, Literature Review & Requirements due |  | 2026-10-16 | 2026-10-16 |  | Deadline |  | ◆
◆ | Milestone | System Analysis & Design due |  | 2026-11-06 | 2026-11-06 |  | Deadline |  |  |  |  | ◆
◆ | Milestone | Implementation (Source Code & Execution) due |  | 2026-11-30 | 2026-11-30 |  | Deadline | [8 empty] | ◆
◆ | Milestone | Final Presentation, Testing & Reports due |  | 2026-12-04 | 2026-12-04 |  | Deadline | [8 empty] | ◆

## By Person
Conflict Intelligence – Project Plan (Gantt Chart)
Ali Hamdy +MIN5_DATA3_S1
The same Gantt chart grouped by person: each member sees only his or her own tasks. # is the task number in the 'Gantt Chart' sheet.
|  | Bar colour = owner: | [5 empty] | Ali |  | Salma |  | Sara |  | Yasmeen |  | Jessy
# | Phase | Task | Owner | Start | End | Days | Status | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07
Ali – Team Lead + Python / Data Analysis
1 | Planning | GitHub Organization (repository, branching, commit & PR rules) | Ali | 2026-10-05 | 2026-10-09 | 5 | Not Started
2 | Planning | Literature Review & Gap Analysis | Ali | 2026-10-05 | 2026-10-16 | 12 | Not Started
3 | Planning | Project Plan & Gantt Chart | Ali | 2026-10-05 | 2026-10-09 | 5 | Not Started
4 | Planning | Project Proposal (problem statement, objectives, scope, expected outcomes) | Ali | 2026-10-05 | 2026-10-09 | 5 | Not Started
5 | Planning | Task Assignment & Roles | Ali | 2026-10-05 | 2026-10-09 | 5 | Not Started
10 | Planning | Lecturer Feedback & Grading Criteria (ongoing: request now, update after each review) | Ali | 2026-10-05 | 2026-12-04 | 61 | Not Started
11 | Planning | Team Follow-up (weekly check-in, handoffs, status) | Ali | 2026-10-05 | 2026-12-04 | 61 | Not Started
12 | Design | Data Quality Assessment & Data Quality Report | Ali | 2026-10-05 | 2026-10-30 | 26 | Not Started
15 | Design | Data Cleaning & Preparation (v0 on 16 Oct, v1 on 23 Oct, final on 30 Oct) | Ali | 2026-10-12 | 2026-10-30 | 19 | Not Started
23 | Implementation | Python EDA | Ali | 2026-10-16 | 2026-11-13 | 29 | Not Started
25 | Implementation | Statistical Analysis | Ali | 2026-10-26 | 2026-11-13 | 19 | Not Started
26 | Implementation | Time-Series, Trend & Seasonality Analysis | Ali | 2026-10-26 | 2026-11-13 | 19 | Not Started
37 | Implementation | Python Documentation | Ali | 2026-11-09 | 2026-11-25 | 17 | Not Started
38 | Implementation | README | Ali | 2026-11-09 | 2026-11-25 | 17 | Not Started
42 | Implementation | Source Code Quality & Code Review | Ali | 2026-11-16 | 2026-11-25 | 10 | Not Started
49 | Final | Testing: Python, Data Quality & Cleaning (own area) | Ali | 2026-11-16 | 2026-11-27 | 12 | Not Started
46 | Implementation | Packaged Final Files | Ali | 2026-11-23 | 2026-11-30 | 8 | Not Started
60 | Final | Final Integration & Consistency Check | Ali | 2026-11-25 | 2026-12-04 | 10 | Not Started
Salma – SQL + Geographic Analysis + Data Validation
6 | Planning | Risk Assessment & Mitigation Plan | Salma | 2026-10-05 | 2026-10-14 | 10 | Not Started
13 | Design | Architecture & Technology Stack | Salma | 2026-10-05 | 2026-10-23 | 19 | Not Started
24 | Implementation | SQL Analysis (CTEs, window functions, subqueries, ranking, aggregations) | Salma | 2026-10-19 | 2026-11-13 | 26 | Not Started
27 | Implementation | Geographic / Spatial Analysis (including geographic SQL) | Salma | 2026-10-26 | 2026-11-20 | 26 | Not Started
28 | Implementation | SQL Analytical Views | Salma | 2026-10-26 | 2026-11-20 | 26 | Not Started
33 | Implementation | SQL Data Validation | Salma | 2026-11-02 | 2026-11-20 | 19 | Not Started
39 | Implementation | SQL Documentation | Salma | 2026-11-09 | 2026-11-20 | 12 | Not Started
40 | Implementation | Cross-Tool Validation (SQL = Python = Power BI = Tableau) | Salma | 2026-11-09 | 2026-11-27 | 19 | Not Started
50 | Final | Technical Documentation (with Jessy's support) | Salma | 2026-11-16 | 2026-12-02 | 17 | Not Started
51 | Final | Testing: SQL & Geographic Analysis (own area) | Salma | 2026-11-16 | 2026-11-27 | 12 | Not Started
63 | Final | Video Demonstration (optional) | Salma | 2026-11-30 | 2026-12-04 | 5 | Not Started
Sara – Power BI + KPI & Dashboard Analytics
7 | Planning | Project KPIs (project success KPIs document) | Sara | 2026-10-05 | 2026-10-14 | 10 | Not Started
16 | Design | Analytical Questions & KPI Design (shortlist on 23 Oct; whole team contributes) | Sara | 2026-10-12 | 2026-10-30 | 19 | Not Started
19 | Design | DFD, Sequence, Activity, State & Class Diagrams | Sara | 2026-10-19 | 2026-11-06 | 19 | Not Started
29 | Implementation | Power Query & Power BI Data Model | Sara | 2026-10-26 | 2026-11-13 | 19 | Not Started
34 | Implementation | Power BI Dashboard Development (slicers, drill-through, tooltips, bookmarks, navigation, UX, performance) | Sara | 2026-11-02 | 2026-11-20 | 19 | Not Started
35 | Implementation | Advanced DAX Measures & KPI Implementation | Sara | 2026-11-02 | 2026-11-20 | 19 | Not Started
43 | Implementation | Dashboard Insights & Recommendations | Sara | 2026-11-16 | 2026-11-24 | 9 | Not Started
44 | Implementation | Power BI Documentation | Sara | 2026-11-16 | 2026-12-02 | 17 | Not Started
52 | Final | Power BI KPI Validation & Dashboard Testing (own area) | Sara | 2026-11-16 | 2026-11-27 | 12 | Not Started
56 | Final | User Manual (Power BI and Tableau dashboards) – provisional owner | Sara | 2026-11-23 | 2026-12-02 | 10 | Not Started
Yasmeen – Database Design + BI Data Modeling + Analytical Results
14 | Design | Database Design (ER Diagram, Logical & Physical Schema) | Yasmeen | 2026-10-05 | 2026-10-23 | 19 | Not Started
20 | Design | Business Rules & KPI Definitions | Yasmeen | 2026-10-19 | 2026-10-30 | 12 | Not Started
30 | Implementation | Database & Data Model Validation | Yasmeen | 2026-10-26 | 2026-11-13 | 19 | Not Started
31 | Implementation | Power BI Data Modeling, Power Query & DAX Support and Validation | Yasmeen | 2026-10-26 | 2026-11-20 | 26 | Not Started
22 | Design | Component Diagram, Deployment Diagram & Deployment Strategy | Yasmeen | 2026-10-28 | 2026-11-06 | 10 | Not Started
41 | Implementation | Database Documentation | Yasmeen | 2026-11-09 | 2026-11-20 | 12 | Not Started
45 | Implementation | Analytical Results (consolidation of findings, key insights, recommendations) | Yasmeen | 2026-11-16 | 2026-11-27 | 12 | Not Started
53 | Final | Testing: Database & Data Model (own area) | Yasmeen | 2026-11-16 | 2026-11-27 | 12 | Not Started
57 | Final | Analytical Results Validation, Limitations & Future Analysis | Yasmeen | 2026-11-23 | 2026-12-02 | 10 | Not Started
61 | Final | Final Presentation (PPT/PDF) | Yasmeen | 2026-11-25 | 2026-12-04 | 10 | Not Started
Jessy – Tableau + Requirements + QA & Documentation
8 | Planning | Dataset Documentation & Data Dictionary | Jessy | 2026-10-05 | 2026-10-14 | 10 | Not Started
9 | Planning | Requirements Gathering (stakeholders, functional & non-functional requirements) | Jessy | 2026-10-05 | 2026-10-16 | 12 | Not Started
17 | Design | QA: Testing Plan | Jessy | 2026-10-12 | 2026-10-30 | 19 | Not Started
18 | Design | Problem Statement Support, Use Case Diagram & Use Case Descriptions | Jessy | 2026-10-12 | 2026-10-27 | 16 | Not Started
21 | Design | Wireframes, Mockups & UI/UX Guidelines | Jessy | 2026-10-19 | 2026-10-30 | 12 | Not Started
32 | Implementation | Tableau Dashboard Development (calculated fields, filters, actions, geographic visualization, UX) | Jessy | 2026-10-26 | 2026-11-20 | 26 | Not Started
36 | Implementation | QA: Test Cases | Jessy | 2026-11-02 | 2026-11-20 | 19 | Not Started
47 | Final | QA: Bug Tracking & Resolution Verification | Jessy | 2026-11-09 | 2026-12-02 | 24 | Not Started
48 | Final | Tableau / Requirements / QA Documentation and Final Documentation Structure | Jessy | 2026-11-09 | 2026-12-02 | 24 | Not Started
54 | Final | Final Project Report | Jessy | 2026-11-16 | 2026-12-04 | 19 | Not Started
55 | Final | Tableau Validation (own area) | Jessy | 2026-11-16 | 2026-11-27 | 12 | Not Started
58 | Final | QA: End-to-End Testing | Jessy | 2026-11-23 | 2026-12-02 | 10 | Not Started
59 | Final | QA: Dashboard Usability Testing | Jessy | 2026-11-23 | 2026-12-02 | 10 | Not Started
62 | Final | QA: Reproducibility Testing | Jessy | 2026-11-26 | 2026-12-02 | 7 | Not Started

## Weekly Plan
Weekly Plan – who works on what, every week
Ali Hamdy +MIN5_DATA3_S1
▶ = starts this week. ✔ = finishes this week. Ongoing tasks (listed at the bottom) run all project long. This sheet is a snapshot of the current dates; if dates change, update it.
Week | Ali | Salma | Sara | Yasmeen | Jessy | Handoffs & official deadlines
Week 1 05 Oct – 11 Oct | ▶ #1 GitHub Organization ✔ ▶ #2 Literature Review & Gap (until 16 Oct) ▶ #3 Project Plan & Gantt ✔ ▶ #4 Project Proposal ✔ ▶ #5 Task Assignment & Roles ✔ ▶ #12 Data Quality Assessment (until 30 Oct) | ▶ #6 Risk Assessment (until 14 Oct) ▶ #13 Architecture & Tech Stack (until 23 Oct) | ▶ #7 Project KPIs (until 14 Oct) | ▶ #14 Database Design (ER & Schema) (until 23 Oct) | ▶ #8 Dataset Documentation (until 14 Oct) ▶ #9 Requirements Gathering (until 16 Oct) | 10 Oct: Jessy → Ali, Yasmeen, Salma: Data Dictionary draft (the data contract)
Week 2 12 Oct – 18 Oct | #2 Literature Review & Gap ✔ #12 Data Quality Assessment (until 30 Oct) ▶ #15 Data Cleaning & Preparation (until 30 Oct) ▶ #23 Python EDA (until 13 Nov) | #6 Risk Assessment ✔ #13 Architecture & Tech Stack (until 23 Oct) | #7 Project KPIs ✔ ▶ #16 Analytical Questions & KPIs (until 30 Oct) | #14 Database Design (ER & Schema) (until 23 Oct) | #8 Dataset Documentation ✔ #9 Requirements Gathering ✔ ▶ #17 QA: Testing Plan (until 30 Oct) ▶ #18 Use Case Diagram & Descriptions (until 27 Oct) | 16 Oct: Ali → everyone: dataset v0 (schema frozen) 16 Oct: Jessy → Sara, Yasmeen, Salma: requirements document 16 Oct: OFFICIAL DEADLINE (Planning, Literature Review, Requirements)
Week 3 19 Oct – 25 Oct | #12 Data Quality Assessment (until 30 Oct) #15 Data Cleaning & Preparation (until 30 Oct) #23 Python EDA (until 13 Nov) | #13 Architecture & Tech Stack ✔ ▶ #24 SQL Analysis (until 13 Nov) | #16 Analytical Questions & KPIs (until 30 Oct) ▶ #19 DFD & Behaviour Diagrams (until 06 Nov) | #14 Database Design (ER & Schema) ✔ ▶ #20 Business Rules & KPI Definitions (until 30 Oct) | #17 QA: Testing Plan (until 30 Oct) #18 Use Case Diagram & Descriptions (until 27 Oct) ▶ #21 Wireframes & UI/UX (until 30 Oct) | 23 Oct: Ali → everyone: dataset v1 23 Oct: Sara → Yasmeen, Jessy: KPI shortlist 23 Oct: Yasmeen → Salma, Sara: database schema 23 Oct: Salma → everyone: architecture
Week 4 26 Oct – 01 Nov | #12 Data Quality Assessment ✔ #15 Data Cleaning & Preparation ✔ #23 Python EDA (until 13 Nov) ▶ #25 Statistical Analysis (until 13 Nov) ▶ #26 Time-Series & Seasonality (until 13 Nov) | #24 SQL Analysis (until 13 Nov) ▶ #27 Geographic Analysis (until 20 Nov) ▶ #28 SQL Analytical Views (until 20 Nov) | #16 Analytical Questions & KPIs ✔ #19 DFD & Behaviour Diagrams (until 06 Nov) ▶ #29 Power Query & Data Model (until 13 Nov) | #20 Business Rules & KPI Definitions ✔ ▶ #30 Database & Model Validation (until 13 Nov) ▶ #31 Power BI Modeling & DAX Support (until 20 Nov) ▶ #22 Component, Deployment & Strategy (until 06 Nov) | #17 QA: Testing Plan ✔ #18 Use Case Diagram & Descriptions ✔ #21 Wireframes & UI/UX ✔ ▶ #32 Tableau Dashboard (until 20 Nov) | 27 Oct: Jessy: use case diagram ready 30 Oct: Ali → everyone: final cleaned dataset 30 Oct: Jessy → Sara: wireframes and mockups 30 Oct: Yasmeen → Sara: business rules and KPI definitions
Week 5 02 Nov – 08 Nov | #23 Python EDA (until 13 Nov) #25 Statistical Analysis (until 13 Nov) #26 Time-Series & Seasonality (until 13 Nov) | #24 SQL Analysis (until 13 Nov) #27 Geographic Analysis (until 20 Nov) #28 SQL Analytical Views (until 20 Nov) ▶ #33 SQL Data Validation (until 20 Nov) | #19 DFD & Behaviour Diagrams ✔ #29 Power Query & Data Model (until 13 Nov) ▶ #34 Power BI Dashboard (until 20 Nov) ▶ #35 DAX & KPI Implementation (until 20 Nov) | #30 Database & Model Validation (until 13 Nov) #31 Power BI Modeling & DAX Support (until 20 Nov) #22 Component, Deployment & Strategy ✔ | #32 Tableau Dashboard (until 20 Nov) ▶ #36 QA: Test Cases (until 20 Nov) | 6 Nov: OFFICIAL DEADLINE (System Analysis & Design)
Week 6 09 Nov – 15 Nov | #23 Python EDA ✔ #25 Statistical Analysis ✔ #26 Time-Series & Seasonality ✔ ▶ #37 Python Documentation (until 25 Nov) ▶ #38 README (until 25 Nov) | #24 SQL Analysis ✔ #27 Geographic Analysis (until 20 Nov) #28 SQL Analytical Views (until 20 Nov) #33 SQL Data Validation (until 20 Nov) ▶ #39 SQL Documentation (until 20 Nov) ▶ #40 Cross-Tool Validation (until 27 Nov) | #29 Power Query & Data Model ✔ #34 Power BI Dashboard (until 20 Nov) #35 DAX & KPI Implementation (until 20 Nov) | #30 Database & Model Validation ✔ #31 Power BI Modeling & DAX Support (until 20 Nov) ▶ #41 Database Documentation (until 20 Nov) | #32 Tableau Dashboard (until 20 Nov) #36 QA: Test Cases (until 20 Nov) ▶ #47 QA: Bug Tracking (until 02 Dec) ▶ #48 Tableau, Req & QA Documentation (until 02 Dec) | 13 Nov: Ali (Python, statistics), Salma (SQL), Yasmeen (database): reference totals and findings
Week 7 16 Nov – 22 Nov | #37 Python Documentation (until 25 Nov) #38 README (until 25 Nov) ▶ #42 Code Quality & Code Review (until 25 Nov) ▶ #49 Test: Python & Cleaning (until 27 Nov) | #27 Geographic Analysis ✔ #28 SQL Analytical Views ✔ #33 SQL Data Validation ✔ #39 SQL Documentation ✔ #40 Cross-Tool Validation (until 27 Nov) ▶ #50 Technical Documentation (until 02 Dec) ▶ #51 Test: SQL & Geographic (until 27 Nov) | #34 Power BI Dashboard ✔ #35 DAX & KPI Implementation ✔ ▶ #43 Dashboard Insights (until 24 Nov) ▶ #44 Power BI Documentation (until 02 Dec) ▶ #52 Test: Power BI & DAX (until 27 Nov) | #31 Power BI Modeling & DAX Support ✔ #41 Database Documentation ✔ ▶ #45 Analytical Results (until 27 Nov) ▶ #53 Test: Database & Model (until 27 Nov) | #32 Tableau Dashboard ✔ #36 QA: Test Cases ✔ #47 QA: Bug Tracking (until 02 Dec) #48 Tableau, Req & QA Documentation (until 02 Dec) ▶ #54 Final Project Report (until 04 Dec) ▶ #55 Test: Tableau (until 27 Nov) | 16 Nov: all code ready for Ali's code review 20 Nov: Sara and Jessy: dashboards done; Salma: geographic results → Yasmeen and Salma (validation)
Week 8 23 Nov – 29 Nov | #37 Python Documentation ✔ #38 README ✔ #42 Code Quality & Code Review ✔ #49 Test: Python & Cleaning ✔ ▶ #46 Packaged Final Files (until 30 Nov) ▶ #60 Final Integration & Consistency (until 04 Dec) | #40 Cross-Tool Validation ✔ #50 Technical Documentation (until 02 Dec) #51 Test: SQL & Geographic ✔ | #43 Dashboard Insights ✔ #44 Power BI Documentation (until 02 Dec) #52 Test: Power BI & DAX ✔ ▶ #56 User Manual (until 02 Dec) | #45 Analytical Results ✔ #53 Test: Database & Model ✔ ▶ #57 Results Validation & Limitations (until 02 Dec) ▶ #61 Final Presentation (until 04 Dec) | #47 QA: Bug Tracking (until 02 Dec) #48 Tableau, Req & QA Documentation (until 02 Dec) #54 Final Project Report (until 04 Dec) #55 Test: Tableau ✔ ▶ #58 QA: End-to-End Testing (until 02 Dec) ▶ #59 QA: Usability Testing (until 02 Dec) ▶ #62 QA: Reproducibility (until 02 Dec) | 24 Nov: Sara: dashboard insights → Yasmeen 25 Nov: Ali: README ready → Jessy (reproducibility from 26 Nov) 27 Nov: Yasmeen: analytical results → Jessy (report), Ali (integration)
Week 9 30 Nov – 04 Dec | #46 Packaged Final Files ✔ #60 Final Integration & Consistency ✔ | #50 Technical Documentation ✔ ▶ #63 Video Demonstration ✔ | #44 Power BI Documentation ✔ #56 User Manual ✔ | #57 Results Validation & Limitations ✔ #61 Final Presentation ✔ | #47 QA: Bug Tracking ✔ #48 Tableau, Req & QA Documentation ✔ #54 Final Project Report ✔ #58 QA: End-to-End Testing ✔ #59 QA: Usability Testing ✔ #62 QA: Reproducibility ✔ | 30 Nov: OFFICIAL DEADLINE (Implementation) 4 Dec: OFFICIAL DEADLINE (Final Presentation, Testing & Reports)
Ongoing | Ali: #10 Lecturer Feedback & Grading Criteria (ongoing: request now, update after each review) Ali: #11 Team Follow-up (weekly check-in, handoffs, status)