| PROJECT SUCCESS KPIs Conflict Intelligence How the team measures success: schedule, data quality, analysis, dashboards and documentation |  |  |
| --- | --- | --- |
| PROGRAM DEPI – Data Analyst Track | ROUND MIN5_DATA3_S1 | TASK #7 OWNER Sara · due 14 Oct 2026 |

# 1  Purpose and Scope

The Conflict Intelligence project is successful if it delivers all four official milestones on time, from a clean and traceable UCDP dataset, with analyses and dashboards that agree across tools and are fully documented. This document defines how the team measures that, using 20 KPIs in five areas.

These are project success KPIs: they judge the project itself. They are separate from the analytical KPIs about conflict (fatalities, countries, violence types), which are designed in task #16 and defined in task #20.

| Program | DEPI – Data Analyst Track (round MIN5_DATA3_S1) |
| --- | --- |
| Duration | 5 Oct – 4 Dec 2026 (9 weeks, 63 tasks) |
| Data | UCDP Georeferenced Event Dataset (GED), raw file kept untouched |
| Team | Ali (lead), Salma, Sara, Yasmeen, Jessy |
| Official deadlines | 16 Oct, 6 Nov, 30 Nov, 4 Dec 2026 |
| Document owner | Sara (task #7, due 14 Oct 2026) |

# 2  KPI Framework

Every KPI has one owner, a numeric target, a named evidence source and a fixed checkpoint, so anyone can verify it without asking. Tables in sections 3–7 use the same columns:

- ID: S = schedule, D = data quality, A = analysis, B = dashboards, C = documentation.

- KPI and definition: what is measured and how it is calculated.

- Target: the value that counts as success.

- Evidence: where the number comes from (Gantt_Chart.xlsx, GitHub, test log, bug log).

- Owner: the member who reports the value, not the only one who works on it.

- Checkpoint: when it is measured. The last two columns, Actual and Status, stay empty until that checkpoint: the owner then writes the measured value and picks the status.

Status is judged with one rule for all KPIs:

| Status | Rule |
| --- | --- |
| Met | Value reaches the target |
| At risk | Value misses the target by 10% or less, or the checkpoint is within 7 days and the work is not started |
| Missed | Value misses the target by more than 10% |

# 3  Schedule KPIs

The team delivers every milestone on its official date and keeps at least 90% of tasks on their planned dates.

| ID | KPI and definition | Target | Evidence | Owner | Checkpoint | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | On-time milestones. Milestones delivered complete by the official deadline, out of 4. | 4 of 4 | Milestone list in the Project Plan | Ali | 16 Oct, 6 Nov, 30 Nov, 4 Dec |  | Not started |
| S2 | On-time task completion. Tasks finished by their planned end date, divided by tasks due so far. | 90% or higher | Gantt_Chart.xlsx (By Person sheet) | Ali | Every Sunday |  | Not started |
| S3 | Task delay. Average working days late across late tasks, and the longest single delay. | Average 3 days or less; longest 5 days or less | Gantt_Chart.xlsx | Ali | Every Sunday |  | Not started |
| S4 | Weekly team follow-up. Weekly progress check-ins held with all five members, out of 9 weeks. | 9 of 9 | Follow-up notes (task #11) | Ali | End of each week |  | Not started |

# 4  Data Quality KPIs

The final dataset must be complete, valid, free of duplicates and rebuildable from the untouched raw UCDP file. Cleaning is delivered in three versions: v0 on 16 Oct, v1 on 23 Oct and final on 30 Oct.

| ID | KPI and definition | Target | Evidence | Owner | Checkpoint | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1 | Critical-field completeness. Share of records with a value in the key fields (event ID, date, country, coordinates, fatality estimate). | 99% or higher | Data Quality Report (task #12) | Ali | v0, v1, final |  | Not started |
| D2 | Duplicate records. Events that appear more than once in the final dataset. | 0 | Python cleaning script | Ali | v1, final |  | Not started |
| D3 | Rule validity. Share of records passing the validation rules (dates in range, valid coordinates, no negative fatalities). | 100% | Validation rules (task #15) | Ali | Final, 30 Oct |  | Not started |
| D4 | Rebuild from raw. Final dataset regenerated from the untouched raw file with the same row count and values. | Pass | Cleaning code and raw-file reference (task #8) | Ali | 30 Oct, re-run 27 Nov |  | Not started |

# 5  Analysis KPIs

The analysis succeeds when all seven analytical questions are answered with evidence and every headline number agrees across Python, SQL and Power BI.

| ID | KPI and definition | Target | Evidence | Owner | Checkpoint | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A1 | Questions answered. Analytical questions answered with a result, method and evidence, out of 7. | 7 of 7 | Analytical Results (task #45) | Yasmeen | 27 Nov |  | Not started |
| A2 | Theme coverage. Required themes covered: trends over time, most affected countries and regions, conflict duration, fatalities, civilian impact, geographic concentration, violence types, parties involved. | 8 of 8 | Analytical Questions list (task #16) | Sara | 30 Nov |  | Not started |
| A3 | Cross-tool agreement. Headline figures that match between Python, SQL and Power BI. | 100% | Cross-Tool Validation (task #40) | Salma | 27 Nov |  | Not started |
| A4 | Insights with limits. Insights that include evidence, a recommendation and a stated limitation. | 100% | Insights and Limitations section | Yasmeen | 2 Dec |  | Not started |

# 6  Dashboard KPIs

The Power BI and Tableau dashboards must show correct numbers, offer the planned interactivity, respond quickly and pass testing with no open critical bug at delivery.

| ID | KPI and definition | Target | Evidence | Owner | Checkpoint | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B1 | KPI accuracy. Dashboard KPI values that match the SQL and Python results. | 100% | KPI validation (task #52) | Sara | 27 Nov |  | Not started |
| B2 | Interactivity delivered. Planned features present and working: slicers, drill-through, tooltips, bookmarks, navigation. | 5 of 5 | Power BI Dashboard (task #34) | Sara | 20 Nov |  | Not started |
| B3 | Responsiveness. Report pages that render within 5 seconds. | 100% of pages | Performance Analyzer log | Sara | 20 Nov |  | Not started |
| B4 | Test pass rate. Executed test cases that pass, with zero open critical bugs at delivery. | 95% or higher; 0 critical | Test cases and bug log (Jessy's QA tasks) | Jessy | 27 Nov, 2 Dec |  | Not started |

# 7  Documentation KPIs

Each member documents their own area, every planned deliverable is handed in, and a new user can rerun the project from the README alone.

| ID | KPI and definition | Target | Evidence | Owner | Checkpoint | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C1 | Area documentation. Areas with complete documentation: Python, SQL, Power BI, Database, Tableau with requirements and QA. | 5 of 5 | Documentation tasks #37, #39, #41, #44, #48 | Jessy | 2 Dec |  | Not started |
| C2 | Deliverable completeness. Deliverables handed in, out of all deliverables listed in the Project Plan. | 100% | Deliverables list in the Project Plan | Ali | 4 Dec |  | Not started |
| C3 | Reproducibility. A person outside the owner's area reruns the project from the README without help. | Pass | Reproducibility test (task #62) | Jessy | 2 Dec |  | Not started |
| C4 | Visible contribution. Members with commits in the GitHub organization every week. | 5 of 5 | GitHub commit history | Ali | Every Sunday |  | Not started |

# 8  KPIs by Team Member

Every task is judged by two tests: it is delivered by its end date, and it meets the quality criterion written beside it. Each member's overall result is the share of their tasks that pass both tests (target: 90% or higher, and 100% for tasks that feed an official deadline). The last two columns, Actual and Status, are filled in by the task owner: the actual delivery date or result against the target, and the status.

## 8.1  Ali – Team Lead and Python / Data Analysis

Ali owns 18 tasks, the most of any member: 6 feed the 16 Oct milestone, 2 run all project long, and his cleaned dataset gates the work of everyone else on 30 Oct.

| # | Task and dates | Quality criterion | Target | Evidence | Depends on | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | GitHub organization, 5–9 Oct | Repository, branching strategy, commit and pull-request rules, folder structure; all documents uploaded | 5 of 5 elements; 100% of documents in GitHub | GitHub repository | None |  | Not started |
| 2 | Literature review & gap analysis, 5–16 Oct | Related studies, existing conflict dashboards, dataset and method background, gap analysis | 4 of 4 parts; each study cited | Review document | None |  | Not started |
| 3 | Project plan & Gantt, 5–9 Oct | Gantt, milestones, deliverables, resources and official deadlines included | 5 of 5 elements; 63 of 63 tasks assigned | Project_Plan.docx, Gantt_Chart.xlsx | None |  | Not started |
| 4 | Project proposal, 5–9 Oct | Problem statement, objectives, scope (in and out), expected outcomes | 4 of 4 elements | Proposal document | None |  | Not started |
| 5 | Task assignment & roles, 5–9 Oct | Every member has responsibilities, tasks, deliverables and dates | 5 of 5 members | Plan, section 2 | #3 |  | Not started |
| 10 | Lecturer feedback, 5 Oct – 4 Dec | Feedback requested before 16 Oct; plan updated after each review | Request sent by 16 Oct; 100% of feedback points answered | Feedback log | None |  | Not started |
| 11 | Team follow-up, 5 Oct – 4 Dec | Weekly meeting held; status updated on the Gantt; handoffs dated | 9 of 9 weeks; Gantt updated within 1 day of each meeting | Follow-up notes | None |  | Not started |
| 12 | Data quality assessment & report, 5–30 Oct | Missing values, duplicates, invalid values, data types, categories, outliers and coordinates checked; before and after report | 7 of 7 checks; report ready 30 Oct | Data Quality Report | Raw UCDP file |  | Not started |
| 15 | Data cleaning & preparation, 12–30 Oct | Versions v0 (16 Oct), v1 (23 Oct), final (30 Oct); validation rules met; reusable code | 3 of 3 versions on time; D1–D4 met | Cleaned dataset, cleaning script | #12 |  | Not started |
| 23 | Python EDA, 16 Oct – 13 Nov | Profiling, univariate, bivariate and multivariate analysis with visualizations | 4 of 4 analysis types; every chart titled and labeled | Notebook | #15 v0 |  | Not started |
| 25 | Statistical analysis, 26 Oct – 13 Nov | Descriptive statistics, distributions, comparisons; tests used only where they have a purpose, each interpreted | 100% of tests justified and interpreted | Notebook | #15 final |  | Not started |
| 26 | Time-series & seasonality, 26 Oct – 13 Nov | Trend, seasonality, major changes, yearly and monthly views | 4 of 4 views | Notebook | #15 final |  | Not started |
| 37 | Python documentation, 9–25 Nov | Cleaning, EDA and analysis documented | 3 of 3 parts | Documentation file | #23, #25, #26 |  | Not started |
| 38 | README, 9–25 Nov | Installation, requirements, configuration, execution guide | 4 of 4 sections; reproducibility test passes | README in GitHub | #62 test |  | Not started |
| 42 | Code quality & review, 16–25 Nov | Structured, commented, modular code; naming standards; error handling; validation checks | 100% of scripts reviewed; 0 open review comments | Pull-request reviews | #15, #23 |  | Not started |
| 49 | Testing: Python, data quality & cleaning, 16–27 Nov | Cleaning and analysis code tested; results written for QA | 100% of tests logged; 0 open critical bugs | Test log | #42 |  | Not started |
| 46 | Packaged final files, 23–30 Nov | Notebooks, SQL, Power BI and Tableau files in one clean release | 4 of 4 file groups; release tagged by 30 Nov | GitHub release | All analysis tasks |  | Not started |
| 60 | Final integration & consistency, 25 Nov – 4 Dec | Same numbers, definitions and terms in every document, dashboard and slide | 0 inconsistencies in the final check | Consistency checklist | #46 |  | Not started |

## 8.2  Salma – SQL, Geographic Analysis and Data Validation

Salma owns 11 tasks. She is the project's cross-tool checker: her #40 compares SQL, Python, Power BI and Tableau, so it is the last gate before the 30 Nov implementation milestone.

| # | Task and dates | Quality criterion | Target | Evidence | Depends on | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6 | Risk assessment & mitigation, 5–14 Oct | Each risk has likelihood, impact, mitigation and contingency | 100% of risks fully described; at least 1 risk per area (schedule, data, tools, team) | Risk register | None |  | Not started |
| 13 | Architecture & technology stack, 5–23 Oct | Flow data, cleaning, database, analysis and dashboards shown; every tool justified | 5 of 5 stages drawn; ready 23 Oct | Architecture diagram | None |  | Not started |
| 24 | SQL analysis, 19 Oct – 13 Nov | Each analytical question answered with joins, CTEs, window functions, subqueries, ranking and aggregations where they fit | 7 of 7 questions answered in SQL | SQL scripts | #14 schema (Yasmeen), #15 final dataset |  | Not started |
| 27 | Geographic analysis, 26 Oct – 20 Nov | Concentration, event density, country and region comparison, trends over time, maps, geographic KPIs | 6 of 6 elements | SQL scripts, maps | #15, #24 |  | Not started |
| 28 | SQL analytical views, 26 Oct – 20 Nov | Reusable views serve every dashboard visual | 100% of dashboard visuals fed by a view; 0 duplicate logic | Views in the database | #24, #14 |  | Not started |
| 33 | SQL data validation, 2–20 Nov | Validation queries run; SQL results compared with Python | 100% of headline results match Python | Validation queries and results | #24, #23 (Ali) |  | Not started |
| 39 | SQL documentation, 9–20 Nov | Analysis, views and validation documented | 3 of 3 parts; every view described | Documentation file | #24, #28, #33 |  | Not started |
| 40 | Cross-tool validation, 9–27 Nov | Total events, total fatalities, yearly trends, country and region counts and main KPIs match in SQL, Python, Power BI and Tableau; every difference investigated, explained and fixed or documented | 100% of headline figures match; 100% of differences explained | Comparison table | #34 (Sara), #32 (Jessy), #23, #24 |  | Not started |
| 50 | Technical documentation, 16 Nov – 2 Dec | Methodology, assumptions, pipeline, architecture, schema, KPI definitions, validation results, reproducibility guide | 8 of 8 sections | Technical document | Jessy's structure (#48), #20 |  | Not started |
| 51 | Testing: SQL & geographic, 16–27 Nov | SQL and geographic analysis tested; results written for QA | 100% of tests logged; 0 open critical bugs | Test log | #24, #27 |  | Not started |
| 63 | Video demonstration (optional), 30 Nov – 4 Dec | Short video shows the dashboards | 1 video, ready 4 Dec | Video file | #34, #32 |  | Not started |

## 8.3  Sara – Power BI and KPI & Dashboard Analytics

Sara owns 10 tasks: one feeds the 16 Oct milestone, two feed 6 Nov, four feed 30 Nov and three feed 4 Dec. Her tasks #52 and #56 depend on Yasmeen's validation (#31) and Jessy's Tableau input.

| # | Task and dates | Quality criterion | Target | Evidence | Depends on | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 7 | Project KPIs, 5–14 Oct | KPIs cover all 5 areas; each has a target, owner, evidence source and checkpoint | 5 of 5 areas; 20 of 20 KPIs complete | This document | None |  | Not started |
| 16 | Analytical Questions & KPI Design, 12–30 Oct | Each analytical question is paired with the KPI or metric that answers it; every member contributed questions | 7 of 7 questions paired; shortlist ready 23 Oct; 5 of 5 members contributed | Question and KPI list | Input from all members |  | Not started |
| 19 | DFD and behaviour diagrams, 19 Oct – 6 Nov | Context DFD, detailed DFD, sequence, activity, state and class diagrams are drawn and match the architecture and ER diagram | 6 of 6 diagrams; 0 mismatches found in review | Diagram files in GitHub | #13 architecture (Salma), #14 ER (Yasmeen) |  | Not started |
| 29 | Power Query & data model, 26 Oct – 13 Nov | Star schema with defined relationships; row counts after load equal the final cleaned dataset | 100% row match; 0 ambiguous relationships | Model view, row-count check | #15 final dataset (30 Oct) |  | Not started |
| 34 | Power BI dashboard, 2–20 Nov | Slicers, drill-through, tooltips, bookmarks and navigation work; every analytical question has a visual | 5 of 5 features; 7 of 7 questions shown; each page loads in 5 s or less | .pbix file, Performance Analyzer log | #29, #35 |  | Not started |
| 35 | DAX measures & KPI implementation, 2–20 Nov | Every KPI from the KPI design is a named, commented measure; time intelligence included | 100% of KPIs as measures; at least 1 yearly comparison measure | .pbix measures list | #16, #20 (Yasmeen) |  | Not started |
| 43 | Dashboard insights, 16–24 Nov | Each insight cites a visual, a number and a recommendation | 7 of 7 insights, one per analytical question | Insights section | #34, #35 |  | Not started |
| 44 | Power BI documentation, 16 Nov – 2 Dec | Model, measures, KPIs and dashboard are documented; every measure has name, formula and purpose | 4 of 4 parts; 100% of measures described | Documentation file in GitHub | #34, #35 |  | Not started |
| 52 | KPI validation & dashboard testing, 16–27 Nov | Dashboard KPIs compared with SQL and Python; every test result and bug recorded | 100% KPI match; 0 open critical bugs | Test log and bug log | #33 SQL validation (Salma), #49 Python tests (Ali) |  | Not started |
| 56 | User manual, 23 Nov – 2 Dec | Covers every dashboard page and filter; a person outside the team completes 3 given tasks using only the manual | 100% of pages covered; 3 of 3 tasks completed | User manual file; tester notes | Tableau part from Jessy, proposed by 28 Nov |  | Not started |

## 8.4  Yasmeen – Database Design, BI Data Modeling and Analytical Results

Yasmeen owns 10 tasks. Her #20 turns Sara's KPI shortlist into precise definitions by 30 Oct, and her #45 consolidates every analyst's findings, so both depend on other members' deadlines.

| # | Task and dates | Quality criterion | Target | Evidence | Depends on | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 14 | Database design, 5–23 Oct | ER diagram, logical and physical schema with tables, attributes, keys, relationships and normalization; data loaded | 4 of 4 design parts; data loaded with 100% row match; ready 23 Oct | ER diagram, schema scripts | #12 data quality findings |  | Not started |
| 20 | Business rules & KPI definitions, 19–30 Oct | A precise definition (formula, filter, unit) for every KPI on Sara's shortlist | 100% of shortlisted KPIs defined; ready 30 Oct | Business rules document | #16 shortlist (23 Oct) |  | Not started |
| 22 | Component, deployment & strategy, 28 Oct – 6 Nov | Component diagram, deployment diagram and short strategy note | 3 of 3 items; ready 6 Nov | Diagram files, note | #13 (Salma) |  | Not started |
| 30 | Database & model validation, 26 Oct – 13 Nov | Database and model checked against the cleaned data | 100% row and total match | Validation log | #14, #15 final |  | Not started |
| 31 | Power BI modeling & DAX support, 26 Oct – 20 Nov | Sara's model, Power Query and DAX reviewed and validated | 100% of measures reviewed; 0 open review issues at 20 Nov | Review log | #29, #35 (Sara) |  | Not started |
| 41 | Database documentation, 9–20 Nov | Database, schema and data model documented | 3 of 3 parts; every table and key described | Documentation file | #14, #30 |  | Not started |
| 45 | Analytical results, 16–27 Nov | Findings with evidence, trends, geographic and category findings, comparisons, recommendations, from each analyst | 100% of findings cite a source; 7 of 7 questions covered | Results document | Findings from Ali, Salma, Sara, Jessy |  | Not started |
| 53 | Testing: database & model, 16–27 Nov | Database and model tested; results written for QA | 100% of tests logged; 0 open critical bugs | Test log | #14, #30 |  | Not started |
| 57 | Results validation, limitations & future analysis, 23 Nov – 2 Dec | Results checked against sources; limitations and future work stated | 100% of results rechecked; at least 1 limitation per question | Validation section | #45 |  | Not started |
| 61 | Final presentation, 25 Nov – 4 Dec | Summary, challenges, solutions and outcomes; numbers match the report | 4 of 4 parts; 0 inconsistent numbers | PPT or PDF | #54 (Jessy), #60 (Ali) |  | Not started |

## 8.5  Jessy – Tableau, Requirements and QA & Documentation

Jessy owns 14 tasks. Two of them, #8 and #9, are due for the 16 Oct milestone, and her QA tasks (#17, #36, #47, #58, #59, #62) decide whether every other member's work counts as tested.

| # | Task and dates | Quality criterion | Target | Evidence | Depends on | Actual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | Dataset documentation & data dictionary, 5–14 Oct | Source, version, coverage, time period, geography, granularity, method, data dictionary, citation, raw-file reference | 10 of 10 elements; 100% of fields in the dictionary | Dataset documentation | None |  | Not started |
| 9 | Requirements gathering, 5–16 Oct | Stakeholder needs, user stories, functional and non-functional requirements (performance, security, usability, reliability) | 4 of 4 requirement groups; each requirement testable | Requirements document | None |  | Not started |
| 17 | QA: testing plan, 12–30 Oct | Test strategy, what is tested and by whom | 5 of 5 areas covered, one owner each; ready 30 Oct | Testing plan | #9 |  | Not started |
| 18 | Use case diagram & descriptions, 12–27 Oct | Problem statement support, use case diagram, a description per use case | 100% of use cases described | Diagram and descriptions | #9, #4 (Ali) |  | Not started |
| 21 | Wireframes, mockups & UI/UX guidelines, 19–30 Oct | Wireframes, mockups, guidelines, colors, typography, accessibility | 6 of 6 elements | Design files | #9 |  | Not started |
| 32 | Tableau dashboard, 26 Oct – 20 Nov | Calculated fields, filters, actions, geographic view, UX | 4 of 4 features; each page loads in 5 s or less | Tableau workbook | #15, #21 |  | Not started |
| 36 | QA: test cases, 2–20 Nov | Scenarios, expected and actual results | At least 1 test case per requirement; 100% executed | Test case sheet | #9, #17 |  | Not started |
| 47 | QA: bug tracking & verification, 9 Nov – 2 Dec | Every bug logged, resolved and verified as fixed | 100% of bugs verified; 0 open critical bugs on 2 Dec | Bug log | #36 |  | Not started |
| 48 | Tableau, requirements & QA documentation, 9 Nov – 2 Dec | Three areas documented; structure of the final documentation set; support for the technical document | 3 of 3 areas; structure shared by 16 Nov | Documentation files | #32, #36 |  | Not started |
| 54 | Final project report, 16 Nov – 4 Dec | Summary, analysis, results, limitations | 4 of 4 sections; 0 numbers that differ from the analysis | Report | #45, #57 (Yasmeen) |  | Not started |
| 55 | Tableau validation, 16–27 Nov | Tableau numbers and interactions validated | 100% of figures match SQL and Python | Test log | #32, #40 (Salma) |  | Not started |
| 58 | QA: end-to-end testing, 23 Nov – 2 Dec | Full flow from raw data to dashboards | 1 full run completed; 0 open critical bugs | Test report | #46 (Ali) |  | Not started |
| 59 | QA: dashboard usability testing, 23 Nov – 2 Dec | Testers outside the team find 3 given answers without help | At least 3 testers; 3 of 3 answers found by each | Usability notes | #34, #32 |  | Not started |
| 62 | QA: reproducibility testing, 26 Nov – 2 Dec | Run everything from a clean environment following the README; same cleaned data and results; dependencies, file paths and Power BI and Tableau sources checked | 1 clean run passes; 100% of results identical | Reproducibility report | #38 (Ali), #46 |  | Not started |

# 9  KPI Calculation Sheet

Each KPI is calculated the same way every time. A value between Met and Missed is At risk. The thresholds below replace the general 10% rule in section 2 where they differ.

| ID | Formula | Data needed | How often | Met when | Missed when |
| --- | --- | --- | --- | --- | --- |
| S1 | Milestones delivered complete on or before the deadline | Submission date of each milestone | At each deadline | 4 of 4 | 3 or fewer |
| S2 | Tasks finished by planned end date ÷ tasks whose planned end has passed × 100 | Status column in Gantt_Chart.xlsx | Weekly | 90% or higher | Below 81% |
| S3 | Average working days late across late tasks; longest single delay | Planned and actual end dates | Weekly | Average 3 or less and longest 5 or less | Average over 4 or longest over 7 |
| S4 | Weekly check-ins held with all 5 members | Follow-up notes | Weekly | 9 of 9 | 7 or fewer |
| D1 | Records with every key field filled ÷ total records × 100 | Cleaned dataset (v0, v1, final) | At each version | 99% or higher | Below 95% |
| D2 | Total rows minus unique event IDs | Final dataset | At v1 and final | 0 | More than 5 |
| D3 | Records passing all validation rules ÷ total records × 100 | Validation rules from task #15 | At final | 100% | Below 98% |
| D4 | Rebuilt dataset compared with final: row count and values | Raw file, cleaning script | 30 Oct, 27 Nov | Identical | Any unexplained difference |
| A1 | Questions with a result, a method and evidence | Analytical Results document | Weekly from 16 Nov | 7 of 7 | 5 or fewer |
| A2 | Required themes covered by at least one analysis | Analytical Questions list | At 30 Nov | 8 of 8 | 6 or fewer |
| A3 | Headline figures that match across tools ÷ figures compared × 100 | Cross-tool comparison table | Weekly from 9 Nov | 100% | Below 90% |
| A4 | Insights with evidence, recommendation and limitation ÷ all insights × 100 | Insights and Limitations section | At 2 Dec | 100% | Below 90% |
| B1 | Dashboard KPIs equal to SQL and Python ÷ all dashboard KPIs × 100 | KPI validation log | At 27 Nov | 100% | Below 90% |
| B2 | Planned interactive features present and working | Dashboard review | At 20 Nov | 5 of 5 | 3 or fewer |
| B3 | Pages rendering in 5 seconds or less ÷ all pages × 100 | Performance Analyzer log | At 20 Nov | 100% | Below 90% |
| B4 | Passed test cases ÷ executed test cases × 100; open critical bugs | Test case sheet, bug log | At 27 Nov and 2 Dec | 95% or higher and 0 critical | Below 85% or any critical bug open |
| C1 | Areas whose documentation is written and reviewed by another member | Documentation files | At 2 Dec | 5 of 5 | 3 or fewer |
| C2 | Deliverables handed in ÷ deliverables listed × 100 | Deliverables list in the Project Plan | Weekly from 23 Nov | 100% | Below 90% |
| C3 | Clean run from the README by someone outside the owner's area | Reproducibility report | At 2 Dec | Pass | Fail on 2 Dec |
| C4 | Members with at least 1 commit that week | GitHub commit history | Weekly | 5 of 5 | 3 or fewer |

# 10  Summary Scorecard

The project is on target when every area is Met at its last checkpoint; update the status after each checkpoint.

| Area | KPIs | Headline target | Lead | Status |
| --- | --- | --- | --- | --- |
| Schedule | S1–S4 | 4 of 4 milestones on time; 90% of tasks on time | Ali | Not started |
| Data quality | D1–D4 | 99% completeness, 0 duplicates, rebuild passes | Ali | Not started |
| Analysis | A1–A4 | 7 of 7 questions answered; 100% cross-tool agreement | Yasmeen | Not started |
| Dashboards | B1–B4 | 100% KPI accuracy; 95% tests pass; 0 critical bugs | Sara | Not started |
| Documentation | C1–C4 | 5 of 5 areas documented; reproducibility passes | Jessy | Not started |

# 11  Monitoring and Escalation

KPI values are updated weekly and reviewed at each of the four official deadlines.

- Weekly: each owner reports their KPI values to Ali at the team follow-up, using the evidence listed in sections 3–7.

- At each deadline: each lead updates the status of their own area in the scorecard (section 10) and records the value reached against each target in their KPI tables.

- Escalation: any KPI marked At risk is raised at the next follow-up with a recovery action and a new date; any KPI marked Missed is raised to the team lead the same day.

- Changes: a target changes only by team agreement, and the change and its reason are noted in this document.