| PROJECT PLAN Conflict Intelligence Timeline, who does what, deliverables, coverage and resources |  |  |
| --- | --- | --- |
| PROGRAM DEPI – Data Analyst Track | ROUND MIN5_DATA3_S1 | PROJECT DURATION 5 Oct – 4 Dec 2026 |

1  Timeline (Gantt Chart)

The project runs from 5 October to 4 December 2026 with 63 tasks. Each member has his or her own block below; bar colour shows the owner and the dashed red lines are the official deadlines. The editable version is the Excel file Gantt_Chart.xlsx (sheets: Gantt Chart, By Person, Weekly Plan).

2  Who Does What

Each member owns the tasks below from start to finish.

| Member | Main role | Tasks (number in the Gantt chart, dates) |
| --- | --- | --- |
| Ali | Team Lead + Python / Data Analysis | #1 GitHub Organization (5 Oct – 9 Oct) #2 Literature Review & Gap (5 Oct – 16 Oct) #3 Project Plan & Gantt (5 Oct – 9 Oct) #4 Project Proposal (5 Oct – 9 Oct) #5 Task Assignment & Roles (5 Oct – 9 Oct) #10 Lecturer Feedback (ongoing) (5 Oct – 4 Dec) #11 Team Follow-up (ongoing) (5 Oct – 4 Dec) #12 Data Quality Assessment (5 Oct – 30 Oct) #15 Data Cleaning & Preparation (12 Oct – 30 Oct) #23 Python EDA (16 Oct – 13 Nov) #25 Statistical Analysis (26 Oct – 13 Nov) #26 Time-Series & Seasonality (26 Oct – 13 Nov) #37 Python Documentation (9 Nov – 25 Nov) #38 README (9 Nov – 25 Nov) #42 Code Quality & Code Review (16 Nov – 25 Nov) #49 Test: Python & Cleaning (16 Nov – 27 Nov) #46 Packaged Final Files (23 Nov – 30 Nov) #60 Final Integration & Consistency (25 Nov – 4 Dec) |
| Salma | SQL + Geographic Analysis + Data Validation | #6 Risk Assessment (5 Oct – 14 Oct) #13 Architecture & Tech Stack (5 Oct – 23 Oct) #24 SQL Analysis (19 Oct – 13 Nov) #27 Geographic Analysis (26 Oct – 20 Nov) #28 SQL Analytical Views (26 Oct – 20 Nov) #33 SQL Data Validation (2 Nov – 20 Nov) #39 SQL Documentation (9 Nov – 20 Nov) #40 Cross-Tool Validation (9 Nov – 27 Nov) #50 Technical Documentation (16 Nov – 2 Dec) #51 Test: SQL & Geographic (16 Nov – 27 Nov) #63 Video Demonstration (30 Nov – 4 Dec) |
| Sara | Power BI + KPI & Dashboard Analytics | #7 Project KPIs (5 Oct – 14 Oct) #16 Analytical Questions & KPIs (12 Oct – 30 Oct) #19 DFD & Behaviour Diagrams (19 Oct – 6 Nov) #29 Power Query & Data Model (26 Oct – 13 Nov) #34 Power BI Dashboard (2 Nov – 20 Nov) #35 DAX & KPI Implementation (2 Nov – 20 Nov) #43 Dashboard Insights (16 Nov – 24 Nov) #44 Power BI Documentation (16 Nov – 2 Dec) #52 Test: Power BI & DAX (16 Nov – 27 Nov) #56 User Manual (23 Nov – 2 Dec) |
| Yasmeen | Database Design + BI Data Modeling + Analytical Results | #14 Database Design (ER & Schema) (5 Oct – 23 Oct) #20 Business Rules & KPI Definitions (19 Oct – 30 Oct) #30 Database & Model Validation (26 Oct – 13 Nov) #31 Power BI Modeling & DAX Support (26 Oct – 20 Nov) #22 Component, Deployment & Strategy (28 Oct – 6 Nov) #41 Database Documentation (9 Nov – 20 Nov) #45 Analytical Results (16 Nov – 27 Nov) #53 Test: Database & Model (16 Nov – 27 Nov) #57 Results Validation & Limitations (23 Nov – 2 Dec) #61 Final Presentation (25 Nov – 4 Dec) |
| Jessy | Tableau + Requirements + QA & Documentation | #8 Dataset Documentation (5 Oct – 14 Oct) #9 Requirements Gathering (5 Oct – 16 Oct) #17 QA: Testing Plan (12 Oct – 30 Oct) #18 Use Case Diagram & Descriptions (12 Oct – 27 Oct) #21 Wireframes & UI/UX (19 Oct – 30 Oct) #32 Tableau Dashboard (26 Oct – 20 Nov) #36 QA: Test Cases (2 Nov – 20 Nov) #47 QA: Bug Tracking (9 Nov – 2 Dec) #48 Tableau, Req & QA Documentation (9 Nov – 2 Dec) #54 Final Project Report (16 Nov – 4 Dec) #55 Test: Tableau (16 Nov – 27 Nov) #58 QA: End-to-End Testing (23 Nov – 2 Dec) #59 QA: Usability Testing (23 Nov – 2 Dec) #62 QA: Reproducibility (26 Nov – 2 Dec) |

3  Cross-Team Responsibilities

Some work is shared. In each case one person leads and the others contribute from their own area.

| Responsibility | Lead | Who contributes | Output |
| --- | --- | --- | --- |
| Analytical Questions & KPIs | Sara | Whole team contributes questions for its technical area. Yasmeen turns the shortlist into Business Rules & KPI Definitions. | Question list and KPI definitions (examples: trends over time, most affected countries / regions, conflict duration, fatalities, civilian impact, geographic concentration, violence types, parties involved) |
| Insights, Recommendations & Limitations | Yasmeen (consolidation) | Ali: Python / statistical findings. Salma: SQL / geographic findings. Sara: Power BI / dashboard insights. Jessy: Tableau / QA evidence. | Key insights, evidence, recommendations, limitations, future analysis |
| Cross-Tool Validation | Salma | Every member validates his or her own tool. | SQL = Python = Power BI = Tableau for total events, total fatalities, yearly trends, country / region counts, major KPIs and key results. Each discrepancy is identified, investigated, explained, then corrected or documented |
| Testing & QA | Jessy | Each member tests his or her own area: Ali: Python, data quality, cleaning. Salma: SQL, geographic analysis. Sara: Power BI, DAX, dashboard. Yasmeen: database, data model. Jessy: Tableau, end-to-end, reproducibility. | Test plan, test cases, results, bug log with resolutions |
| Documentation | Jessy (structure only) | SQL: Salma. Python: Ali. Power BI: Sara. Database: Yasmeen. Tableau, requirements, QA: Jessy. | Each owner writes the documentation of his or her own area; Jessy does not write everybody's technical documentation |
| Dataset Documentation | Jessy | Ali, Salma and Yasmeen verify technical details. | Source, version, description, coverage, time period, geographic coverage, granularity, collection methodology, data dictionary, citation, reference to the untouched raw dataset |
| Problem Statement & Objectives | Ali (in the Proposal) | Jessy supports the requirements / system analysis side. | Problem statement, objectives, scope, out of scope, expected outcomes |

4  Milestones

| Date | Milestone | What must be ready |
| --- | --- | --- |
| 16 Oct 2026 | Planning, Literature Review & Requirements | Project Proposal, Project Plan & Gantt, Task Assignment, GitHub organization, Risk Assessment, Project KPIs, Dataset Documentation & Data Dictionary, Literature Review & Gap Analysis, lecturer feedback request, Requirements Gathering |
| 6 Nov 2026 | System Analysis & Design | Data Quality Report and cleaned dataset (30 Oct), problem statement and use case diagram, architecture and technology stack, ER diagram and schema, analytical questions and KPI design, business rules and KPI definitions, wireframes and UI/UX, DFD and behaviour diagrams, component / deployment diagrams and strategy, testing plan |
| 30 Nov 2026 | Implementation (Source Code & Execution) | EDA, statistics, time-series, SQL analysis / views / validation, geographic analysis, database validation, Power BI and Tableau dashboards, dashboard insights, analytical results, cross-tool validation, code quality review, Python / SQL / database documentation, README, packaged final files, commit history |
| 4 Dec 2026 | Final Presentation, Testing & Reports | Own-area testing, test cases, bug tracking, end-to-end, usability and reproducibility testing, results validation, limitations and future analysis, technical documentation, Power BI and Tableau / QA documentation, user manual, final report, final presentation, final integration, optional video |

5  Tasks & Deliverables

All 63 tasks with owner, dates and what each one must include. Task 'ongoing' means it runs all project long.

| # | Task / deliverable | Owner | Dates | Must include |
| --- | --- | --- | --- | --- |
| 1 | GitHub Organization (repository, branching, commit & PR rules) | Ali | 5 Oct – 9 Oct | Repository, branching strategy, meaningful commits, pull-request descriptions, folder structure, all documents uploaded to GitHub |
| 2 | Literature Review & Gap Analysis | Ali | 5 Oct – 16 Oct | Related studies, existing conflict dashboards / solutions, dataset and methodology background, gap analysis |
| 3 | Project Plan & Gantt Chart | Ali | 5 Oct – 9 Oct | Gantt chart, milestones, deliverables, resource allocation, official deadlines |
| 4 | Project Proposal (problem statement, objectives, scope, expected outcomes) | Ali | 5 Oct – 9 Oct | Problem statement, project objectives, project scope (in / out), expected outcomes |
| 5 | Task Assignment & Roles | Ali | 5 Oct – 9 Oct | Responsibilities, tasks, deliverables and dates of every member |
| 6 | Risk Assessment & Mitigation Plan | Salma | 5 Oct – 14 Oct | Risks, likelihood, impact, mitigation and contingency |
| 7 | Project KPIs (project success KPIs document) | Sara | 5 Oct – 14 Oct | Project success KPIs: schedule, data quality, analysis, dashboards, documentation |
| 8 | Dataset Documentation & Data Dictionary | Jessy | 5 Oct – 14 Oct | UCDP source, dataset version, coverage and time period, geographic coverage, granularity, collection methodology, data dictionary, citation, raw untouched dataset reference |
| 9 | Requirements Gathering (stakeholders, functional & non-functional requirements) | Jessy | 5 Oct – 16 Oct | Stakeholder requirements, user stories, functional requirements, non-functional requirements (performance, security, usability, reliability), requirements documentation |
| 10 | Lecturer Feedback & Grading Criteria (ongoing: request now, update after each review) | Ali | ongoing 5 Oct – 4 Dec | Feedback & evaluation, suggested improvements, final grading criteria, updates after each lecturer review |
| 11 | Team Follow-up (weekly check-in, handoffs, status) | Ali | ongoing 5 Oct – 4 Dec | Weekly meeting, task status on the Gantt, dated handoffs between members |
| 12 | Data Quality Assessment & Data Quality Report | Ali | 5 Oct – 30 Oct | Missing values, duplicates, invalid values, data types, category consistency, outliers, coordinate validation, before / after report |
| 13 | Architecture & Technology Stack | Salma | 5 Oct – 23 Oct | Project architecture (data → cleaning → database → analysis → dashboards) and technology stack |
| 14 | Database Design (ER Diagram, Logical & Physical Schema) | Yasmeen | 5 Oct – 23 Oct | ER diagram, logical schema, physical schema, tables, attributes, keys, relationships, normalization, loading the data |
| 15 | Data Cleaning & Preparation (v0 on 16 Oct, v1 on 23 Oct, final on 30 Oct) | Ali | 12 Oct – 30 Oct | Cleaning process, transformations, feature engineering, merging / aggregation, validation rules, final analysis-ready dataset, reusable code |
| 16 | Analytical Questions & KPI Design (shortlist on 23 Oct; whole team contributes) | Sara | 12 Oct – 30 Oct | The 7 analytical questions plus parties, and the KPI / metric that answers each one |
| 17 | QA: Testing Plan | Jessy | 12 Oct – 30 Oct | Test strategy and plan, what is tested and by whom |
| 18 | Problem Statement Support, Use Case Diagram & Use Case Descriptions | Jessy | 12 Oct – 27 Oct | Problem statement (supporting Ali), use case diagram, use case descriptions |
| 19 | DFD, Sequence, Activity, State & Class Diagrams | Sara | 19 Oct – 6 Nov | Context-level and detailed DFD, sequence, activity, state and class diagrams (adapted to a data project) |
| 20 | Business Rules & KPI Definitions | Yasmeen | 19 Oct – 30 Oct | Business rules and the precise definition of every KPI (from Sara's shortlist) |
| 21 | Wireframes, Mockups & UI/UX Guidelines | Jessy | 19 Oct – 30 Oct | Wireframes, mockups, UI/UX guidelines, color scheme, typography, accessibility |
| 22 | Component Diagram, Deployment Diagram & Deployment Strategy | Yasmeen | 28 Oct – 6 Nov | Component diagram, deployment diagram, short deployment strategy note |
| 23 | Python EDA | Ali | 16 Oct – 13 Nov | Data profiling, univariate, bivariate and multivariate analysis, visualizations |
| 24 | SQL Analysis (CTEs, window functions, subqueries, ranking, aggregations) | Salma | 19 Oct – 13 Nov | Analytical questions, advanced joins, CTEs, window functions, subqueries, ranking, aggregations |
| 25 | Statistical Analysis | Ali | 26 Oct – 13 Nov | Descriptive statistics, distributions, comparisons, tests only where they have a purpose, interpretation |
| 26 | Time-Series, Trend & Seasonality Analysis | Ali | 26 Oct – 13 Nov | Trend over time, seasonal patterns, major changes, yearly and monthly views |
| 27 | Geographic / Spatial Analysis (including geographic SQL) | Salma | 26 Oct – 20 Nov | Geographic concentration, event density, country / region comparison, geographic trends over time, maps, geographic KPIs |
| 28 | SQL Analytical Views | Salma | 26 Oct – 20 Nov | Reusable analytical views for the dashboards |
| 29 | Power Query & Power BI Data Model | Sara | 26 Oct – 13 Nov | Power Query transformations, data model (star schema), relationships |
| 30 | Database & Data Model Validation | Yasmeen | 26 Oct – 13 Nov | Database and data model checked against the cleaned data |
| 31 | Power BI Data Modeling, Power Query & DAX Support and Validation | Yasmeen | 26 Oct – 20 Nov | Supports and validates Sara's data model, Power Query and DAX |
| 32 | Tableau Dashboard Development (calculated fields, filters, actions, geographic visualization, UX) | Jessy | 26 Oct – 20 Nov | Calculated fields, interactive filters, dashboard actions, geographic visualization, Tableau dashboard UX |
| 33 | SQL Data Validation | Salma | 2 Nov – 20 Nov | Validation queries, SQL results checked against Python |
| 34 | Power BI Dashboard Development (slicers, drill-through, tooltips, bookmarks, navigation, UX, performance) | Sara | 2 Nov – 20 Nov | Interactive filters and slicers, drill-through, tooltips, bookmarks, navigation, dashboard UX, performance optimization |
| 35 | Advanced DAX Measures & KPI Implementation | Sara | 2 Nov – 20 Nov | DAX measures, KPI measures, time intelligence |
| 36 | QA: Test Cases | Jessy | 2 Nov – 20 Nov | Test scenarios, expected results, actual results |
| 37 | Python Documentation | Ali | 9 Nov – 25 Nov | Python analysis, cleaning and EDA documentation |
| 38 | README | Ali | 9 Nov – 25 Nov | Installation steps, system requirements, configuration instructions, execution guide |
| 39 | SQL Documentation | Salma | 9 Nov – 20 Nov | SQL analysis, views and validation documentation |
| 40 | Cross-Tool Validation (SQL = Python = Power BI = Tableau) | Salma | 9 Nov – 27 Nov | Total events, total fatalities, yearly trends, country / region counts, major KPIs, key results; every discrepancy identified, investigated, explained and corrected or documented |
| 41 | Database Documentation | Yasmeen | 9 Nov – 20 Nov | Database, schema and data model documentation |
| 42 | Source Code Quality & Code Review | Ali | 16 Nov – 25 Nov | Structured and commented code, coding standards, naming, modular reusable code, security practices, validation checks, error and exception handling |
| 43 | Dashboard Insights & Recommendations | Sara | 16 Nov – 24 Nov | Insights and recommendations that come from the Power BI dashboard |
| 44 | Power BI Documentation | Sara | 16 Nov – 2 Dec | Model, measures, KPIs and dashboard documentation |
| 45 | Analytical Results (consolidation of findings, key insights, recommendations) | Yasmeen | 16 Nov – 27 Nov | Key findings with evidence, trends, geographic findings, category / conflict findings, comparisons, recommendations (findings come from each analyst) |
| 46 | Packaged Final Files | Ali | 23 Nov – 30 Nov | Final notebooks, SQL, Power BI and Tableau files in one clean release; published dashboard link only if the team publishes |
| 47 | QA: Bug Tracking & Resolution Verification | Jessy | 9 Nov – 2 Dec | Bug log, resolutions, verification that each bug is fixed |
| 48 | Tableau / Requirements / QA Documentation and Final Documentation Structure | Jessy | 9 Nov – 2 Dec | Tableau, requirements and QA documentation; structure of the final documentation; support for the technical documentation |
| 49 | Testing: Python, Data Quality & Cleaning (own area) | Ali | 16 Nov – 27 Nov | Tests of the cleaning and analysis code, results written for the QA process |
| 50 | Technical Documentation (with Jessy's support) | Salma | 16 Nov – 2 Dec | Methodology, assumptions, pipeline, system architecture, database schema, KPI definitions, validation results, reproducibility guide |
| 51 | Testing: SQL & Geographic Analysis (own area) | Salma | 16 Nov – 27 Nov | Tests of the SQL and geographic analysis, results written for the QA process |
| 52 | Power BI KPI Validation & Dashboard Testing (own area) | Sara | 16 Nov – 27 Nov | KPI validation, dashboard testing, validation against SQL / Python results |
| 53 | Testing: Database & Data Model (own area) | Yasmeen | 16 Nov – 27 Nov | Tests of the database and data model, results written for the QA process |
| 54 | Final Project Report | Jessy | 16 Nov – 4 Dec | Final project report: summary of the project, analysis, results and limitations |
| 55 | Tableau Validation (own area) | Jessy | 16 Nov – 27 Nov | Tableau numbers and interactions validated |
| 56 | User Manual (Power BI and Tableau dashboards) – provisional owner | Sara | 23 Nov – 2 Dec | Instructions for end users of the dashboards (Jessy supplies the Tableau part) |
| 57 | Analytical Results Validation, Limitations & Future Analysis | Yasmeen | 23 Nov – 2 Dec | Results checked against the sources, limitations, future analysis opportunities |
| 58 | QA: End-to-End Testing | Jessy | 23 Nov – 2 Dec | Full flow from raw data to dashboards |
| 59 | QA: Dashboard Usability Testing | Jessy | 23 Nov – 2 Dec | At least 3 testers outside the team find 3 given answers in the dashboards without help |
| 60 | Final Integration & Consistency Check | Ali | 25 Nov – 4 Dec | Same numbers, definitions and terms in every document, dashboard and slide |
| 61 | Final Presentation (PPT/PDF) | Yasmeen | 25 Nov – 4 Dec | Summary of the project, challenges, solutions, outcomes |
| 62 | QA: Reproducibility Testing | Jessy | 26 Nov – 2 Dec | Run everything from a clean environment following the README, same cleaned data and results, dependencies, file paths, Power BI and Tableau sources |
| 63 | Video Demonstration (optional) | Salma | 30 Nov – 4 Dec | Short video of the dashboards |

6  DEPI Coverage Matrix

| DEPI requirement | Assigned | Deliverable |
| --- | --- | --- |
| Project Proposal | Ali | Project proposal (problem statement, objectives, scope,outcomes) |
| Project Plan (Gantt, milestones, deliverables, resources) | Ali | Project_Plan.docx, Gantt_Chart.xlsx |
| Task Assignment & Roles | Ali | Task Assignment & Roles document |
| Risk Assessment & Mitigation Plan | Salma | Risk Assessment & Mitigation Plan |
| KPIs (project KPIs) | Sara | Project KPIs document |
| Feedback & Evaluation | Ali | Lecturer feedback file |
| Suggested Improvements | Ali | Same file, updated after each review |
| Final Grading Criteria | Ali | Same file |
| Stakeholder Analysis | Jessy | Requirements document |
| User Stories & Use Cases | Jessy | Requirements document |
| Functional Requirements | Jessy | Requirements document |
| Non-functional Requirements | Jessy | Requirements document |
| Problem Statement & Objectives | Ali | Project Proposal + system analysis |
| Use Case Diagram & Descriptions | Jessy | Use case diagram and descriptions |
| Functional & Non-Functional Requirements (restated) | Jessy | Reuses the requirements document |
| Software Architecture | Salma | Architecture diagram (data → cleaning → database → analysis → dashboards) |
| ER Diagram | Yasmeen | ERD |
| Logical & Physical Schema | Yasmeen | Schema document |
| DFD (context + detailed) | Sara | DFD levels |
| Sequence Diagrams | Sara | Sequence diagram |
| Activity Diagram | Sara | Activity diagram |
| State Diagram | Sara | State diagram |
| Class Diagram | Sara | Class diagram |
| Wireframes & Mockups | Jessy | Wireframes and mockups |
| UI/UX Guidelines | Jessy | UI/UX guidelines |
| Technology Stack | Salma | Technology stack section |
| Deployment Diagram | Yasmeen | Deployment diagram |
| Component Diagram | Yasmeen | Component diagram |
| Testing & Validation (plan) | Jessy | Testing plan |
| Deployment Strategy | Yasmeen | Deployment strategy note |
| Structured & Well-Commented Code | Ali | Code quality review |
| Coding Standards & Naming Conventions | Ali | Code quality review |
| Modular Code & Reusability | Ali | Code quality review |
| Security & Error Handling | Ali | Validation checks and error handling review |
| Version Control Repository | Ali | GitHub repository |
| Branching Strategy | Ali | GitHub organization rules |
| Commit History & Documentation | All members | Commits and pull-request descriptions |
| Installation steps | Ali | README |
| System requirements | Ali | README |
| Configuration instructions | Ali | README |
| Execution guide | Ali | README |
| Executable files / packaged application | Ali | Packaged final files |
| Deployed app / published dashboard link (if used) | Sara | Published link only if the team publishes |
| Test Cases & Test Plan | Jessy | Testing plan and test cases |
| Automated Testing (if applicable) | Ali (stretch) | Automated data-quality checks, only if time allows |
| Bug Reports | Jessy | Bug log and resolutions |
| User Manual | Sara (provisional) | User manual of the dashboards (see the note below the table) |
| Technical Documentation | Salma | Technical documentation |
| Project Presentation (PPT/PDF) | Yasmeen | Final presentation |
| Video Demonstration (optional) | Salma | Video demo |

7  Project Workflow

| Step | Stage | Led by |
| --- | --- | --- |
| 1 | Project Planning | Ali |
| 2 | Literature Review | Ali |
| 3 | Requirements Gathering | Jessy |
| 4 | Dataset Documentation & Data Understanding | Jessy |
| 5 | Data Quality Assessment | Ali |
| 6 | Data Cleaning & Preparation | Ali |
| 7 | Database Design & SQL | Yasmeen, Salma |
| 8 | Python EDA & Statistical Analysis | Ali |
| 9 | Time-Series / Trend / Seasonality Analysis | Ali |
| 10 | Geographic / Spatial Analysis | Salma |
| 11 | KPI & Analytical Questions | Sara (team) |
| 12 | Power BI | Sara (Yasmeen supports) |
| 13 | Tableau | Jessy |
| 14 | Cross-Tool Validation | Salma (all) |
| 15 | Analytical Results | Yasmeen |
| 16 | Insights + Recommendations + Limitations | Yasmeen (all analysts) |
| 17 | Testing & QA | Jessy (all) |
| 18 | Reproducibility | Jessy |
| 19 | Documentation | Each owner (Jessy: structure) |
| 20 | Final Presentation & Delivery | Yasmeen, Ali |

8  Tools & Technologies

| Need | Tools | Used for |
| --- | --- | --- |
| Planning & documents | Word, Excel (Gantt chart), PowerPoint, GitHub | Proposal, plan, documents, presentation |
| Data preparation & analysis | Python (pandas) | Quality assessment, cleaning, EDA, statistics, time-series |
| Database & SQL | SQL database | Schema, queries, analytical views, validation |
| Geographic analysis | Python, SQL, Tableau | Maps, density, geographic KPIs |
| Dashboards | Power BI + DAX, Tableau | Interactive dashboards |
| Design & diagrams | A diagramming tool, wireframing tool | UML / ER / DFD diagrams, wireframes, mockups |
| Collaboration & delivery | GitHub | Version control, documentation, release |

9  Data, Time, People & Budget

| Data | UCDP Georeferenced Event Dataset (GED), downloaded from https://ucdp.uu.se/downloads/#ged_global. The original file is kept untouched. |
| --- | --- |
| Time | 9 weeks (5 Oct – 4 Dec 2026), with 4 official deadlines |
| People | 5 team members (section 2) |
| Budget | No monetary budget assumed. The team's own devices and the tools above are used. |